## Overview (hidden)
Row Labels | Count of Process Stage
Awaiting Implementation | 5
Consultation | 3
Final Assessment | 2
Initial Assessment | 11
Preliminary Assessment | 5
REC Party Impact Assessment | 1
Service Provider Impact Assessment | 1
Solution Development | 8
(blank)
Grand Total | 36

## Live CP Register
Change Proposal Reference | Change Proposal Title | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Priority Status | Priority Score | Change Path | Responsible Committee | Proposed Implementation Date | Fuel | Impacted Parties | Process Stage | Next Activity | Next Activity Due Date | On Track (RAG)
R0006 | Missing Meter Technical Details | Link | Diane Lyon | Scottish Power Energy Retail | Elise Handy | 2021-09-07 | 2b (Cat 2 products with technical impacts) | Low | 98 | Self-Governance | Change Panel | TBD | Elec | Energy Suppliers, Metering Equipment Managers, Data Collectors | Impact Assessment | REC Party Impact Assessment due to close | 2023-02-24
R0009 | Introduction of SDEP and EES User Maintenance API | Link | Joanne Haran David Morley | Pure Planet OVO | Jonathan Holland | 2021-09-08 | 2b (Cat 2 products with technical impacts) | n/a | n/a | Self-Governance | Technical Expert Panel | 2023-11-03 | Elec and Gas | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers, EES Users | Final Assessment | Final Change Report presented to TEP for decision | 2023-02-22
R0010 | New Meter Types for Auxiliary Proportional Controllers (APCs) | Link | David Morton | EDF | Jonathan Holland | 2021-09-08 | 1b (Cat 1 products with technical impacts) | n/a | n/a | Self-Governance | Technical Expert Panel | 2023-06-30 | Elec | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers, DCC, Data Collectors, EES Users, Prepayment Meter Infrastructure Provider, Meter Point Administration Service | Awaiting Implementation | Implementation | 2023-06-30
R0011 | Reporting of additional EMR Backing Data to Suppliers | Link | Ben Lathbury | EMRS | Gemma Dixon | 2021-09-08 | 1b (Cat 1 products with technical impacts) | n/a | n/a | Self-Governance | Technical Expert Panel | 2023-06-30 | Elec | Energy Suppliers | Awaiting Implementation | Implementation | 2023-06-30
R0015 | Remote communication obligations for electricity Advanced Meters | Link | David Brown (originally Tom Chevalier) | Association of Meter Operators | Harriet Truss | 2021-11-17 | 1a (Cat 1 products without technical impacts) | n/a | n/a | Self-Governance | Metering Expert Panel | 2023-06-30 | Elec | Energy Suppliers, Metering Equipment Managers, Data Collectors | Final Assessment | FCR published | 2023-02-14
R0016 | Resolution of Bilateral Erroneous Transfers | Link | Ben Atkinson | British Gas | Gemma Dixon | 2021-11-17 | 1b (Cat 1 products with technical impacts) | Low | 61 | Self-Governance | Change Panel | TBD | Elec and Gas | Energy Suppliers, EES Provider | Solution Development | Present Re-baseline plan to Change Panel | 2023-04-18
R0017 | Invalid Requests for Site Technical Details | Link | Elaine Carr | Scottish Power Energy Networks | Ann Perry | 2021-11-22 | 1b (Cat 1 products with technical impacts) | Low | 91 | Self-Governance | Metering Expert Panel | TBD | Elec | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | Preliminary Assessment | IA closed, Preliminary Change Report due to be published 24/02/23 | 2023-02-24
R0021 | Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2021-12-09 | 2b (Cat 2 products with technical impacts) | n/a | n/a | Authority-Approval | Metering Expert Panel | 2023-06-30 | Elec | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | Awaiting Implementation | Implementation | 2023-06-30
R0022 | Amendment to REC Data Access Matrix | Link | Harriet Truss | Code Manager | Harriet Truss | 2021-12-15 | 1b (Cat 1 products with technical impacts) | n/a | n/a | Self-Governance | Change Panel | 2022-11-04 | Elec and Gas | EES Users | Awaiting Implementation | Implementation of Technical solution | 2023-04-01
R0025 | Service Provider Performance Charges (DCC) | Link | Eliana Campbell | Code Manager | Gemma Dixon | 2022-01-04 | 1a (Cat 1 products without technical impacts) | Medium | 118 | Authority-Approval | Performance Assurance Board | 2023-04-01 | n/a | DCC | Awaiting Implementation | Ofgem approved | 2023-04-01
R0026 | Whole current (WC)/Current Transformer (CT) certificates | Link | Courtney Campbellwood | Code Manager | Ann Perry | 2022-01-06 | 1a (Cat 1 products without technical impacts) | Medium | 103 | Self-Governance | Metering Expert Panel | TBD | Elec | Metering Equipment Managers | On Hold | On Hold - update to be shared with CP on 07/02/2023 | 2023-03-01
R0030 | Erroneous Transfer Cancellations | Link | Lorna Mallon | Scottish Power Energy Retail | Gemma Dixon | 2022-01-14 | 1b (Cat 1 products with technical impacts) | n/a | n/a | Self-Governance | Change Panel | 2023-06-30 | Elec and Gas | Energy Suppliers | Awaiting Implementation | Implementation | 2023-06-30
R0032 | New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS) | Link | Colette Baldwin | Code Manager | Gemma Dixon | 2022-02-03 | 1b (Cat 1 products with technical impacts) | n/a | n/a | Self-Governance | Change Panel | 2023-06-30 | Elec | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers, EES Users | Awaiting Implementation | Implementation | 2023-06-30
R0037 | Prepayment Credit Balance & Debt Transfer Processes | Link | Andy Knowles | Utilita | Gemma Dixon | 2022-03-10 | 1b (Cat 1 products with technical impacts) | Medium | 123 | Authority-Approval | Change Panel | TBD | Elec and Gas | Energy Suppliers | Impact Assessment | Service Provider Impact Assessment issued to SDES Provider on 30/01/2023 - Party IA to be issued on 20/02/2023 | 2023-04-14
R0043 | Commissioning of Works using shared Meter Operator services by the Crowded Meter Room Co-ordinator (CMRC) | Link | David Jones | Alt HanCo | Gemma Dixon | 2022-04-21 | 1a (Cat 1 products without technical impacts) | Medium | 118 | Authority-Approval | Change Panel | TBD | Elec | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers, Data Collectors, Meter Asset Providers | Solution Development | Present Re-baseline plan to Change Panel | 2023-06-06
R0044 | MHHS Programme Changes required to Central Switching Service | Link | Jason Brogden | MHHS Programme | Harriet Truss | 2022-04-29 | 1b (Cat 1 products with technical impacts) | Medium | 110 | Authority-Approval | Change Panel | MHHS M8 | Elec | DCC as CSS Provider, (Distribution Network Operators as ERDS Providers) | Awaiting Implementation | Approved by Ofgem 02/02/2023
R0047 | Metering Code of Practice Consolidation Review | Link | Aiyesha Andrade | RECCo | Ann Perry | 2022-05-20 | 1a (Cat 1 products without technical impacts) | n/a | n/a | Self-Governance | Change Panel | 2023-04-01 | Elec and Gas | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | Awaiting Implementation | Implementation | 2023-04-01
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | Link | Cordelia Grey | DCC | Gemma Dixon | 2022-05-20 | 2a (Cat 2 products without technical impacts) | Low | 34 | Self-Governance | Technical Expert Panel | 2023-06-30 | n/a | DCC | Preliminary Assessment | PCR Publication | 2023-02-17
R0049 | Intellectual Property Rights and Services Data Main Body changes | Link | Cordelia Grey | DCC | Jonathan Holland | 2022-05-20 | 1a (Cat 1 products without technical impacts) | Low | 37 | Self-Governance | Change Panel | TBD | n/a | DCC | Initial Assessment | Code Manager to develop Change Proposal Plan once the proposed legal text changes have been approved | 2023-02-24
R0051 | Switch Request Objections (Change of Occupier) | Link | Simon Askew | Business Energy Direct | Jonathan Holland | 2022-05-24 | TBD | Low | 70 | Self-Governance | TBD | TBD | n/a | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0052 | GES Service Definition Document | Link | Cristina Bermudez Alvarez | Code Manager | Elise Handy | 2022-06-13 | 2a (Cat 2 products without technical impacts) | Low | 57 | Self-Governance | Technical Expert Panel | 2023-02-24 | Gas | GES Provider, Metering Equipment Managers, Meter Asset Providers | Awaiting Implementation | Awaiting Implementation | 2023-02-24
R0053 | 24/7 Emergency Metering Service | Link | Bryan Heap | Electricity North West Limited | Jonathan Holland | 2022-06-15 | TBD | Medium | 136 | Self-Governance | TBD | TBD | n/a | TBD | Initial Assessment | RFI closed - results will be reviewed by the Code Manager to help formulate the Change Proposal Plan | 2023-02-24
R0054 | EES Access for Virtual Lead Parties | Link | Ann Perry | Code Manager | George Barnes | 2022-06-17 | 2b (Cat 2 products with technical impacts) | n/a | n/a | Self-Governance | Technical Expert Panel | 2022-11-04 | Elec | EES Provider, Virtual Lead Parties | Awaiting Implementation | Implementation of Technical solution | 2023-04-01
R0055 | Switching Operator Outage Notification Lead time | Link | Cordelia Grey | DCC | Ann Perry | 2022-07-06 | 2a (Cat 2 products without technical impacts) | n/a | n/a | Self-Governance | Technical Expert Panel | 2023-02-24 | Elec and Gas | DCC, GRDS Provider, ERDS Providers, EES Provider, GES Provider | Awaiting Implementation | Awaiting Implementation | 2023-02-24
R0056 | EES/GES Additional Service Request for Housing Associations to be added to the Data Access Matrix | Link | Fay Morris | Correla Limited | Jonathan Holland | 2022-07-05 | 2b (Cat 2 products with technical impacts) | Low | 53 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0057 | Clarification of Supplier of Last Resort Obligations under the REC | Link | Paul Saker | EDF | Elise Handy | 2022-07-15 | 2a (Cat 2 products without technical impacts) | Low | 48 | Self-Governance | Change Panel | 2023-11-03 | Elec and Gas | Energy Suppliers, Metering Equipment Managers, Data Collectors, Data Aggregators | Consultation | Consultation published on 10/02/2023. Due to close on 03/03/2023 | 2023-03-03
R0058 | REC Services Procurement Clarification | Link | Cordelia Grey | DCC | Jonathan Holland | 2022-07-26 | TBD | Low | 27 | TBD | TBD | TBD | TBD | DCC, RECCo | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0059 | Maintenance of Qualification Schedule Change | Link | Georgina Scott-Picton | Code Manager | Jonathan Holland | 2022-08-05 | 1a (Cat 1 products without technical impacts) | Low | 61 | Self-Governance | Performance Assurance Board | TBD | Elec and Gas | All REC Service Users | Solution Development | Solution Development activity to be completed | 2023-03-01
R0060 | ERDS Service Definition time zone correction | Link | Daniel Tadecicco | St Clements | Harriet Truss | 2022-08-11 | TBD | Low | 26 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0061 | Resolution of invalid CSS data by Data Owners | Link | Daniel Tadecicco | St Clements | Gemma Dixon | 2022-08-11 | TBD | Medium | 118 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0062 | Removal of ERDA meteringPointEnergyFlow change restriction | Link | Daniel Tadecicco | St Clements | Harriet Truss | 2022-08-11 | TBD | Low | 77 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0063 | Addition of key information to all Service Now tickets | Link | Chris Price | St Clements | Elise Handy | 2022-08-22 | 2b (Cat 2 products with technical impacts) | Medium | 124 | Self-Governance | Technical Expert Panel | TBD | n/a | Switching Data Service Providers, Central Switching Service Provider | Solution Development | Service Provider PIA to be issued 27 February | 2023-02-27
R0064 | Creating a Meter Operator Agent and MOCoP Installer | Link | Anton Moden | Code Manager | Jonathan Holland | 2022-08-22 | 1b (Cat 1 products with technical impacts) | Medium | 135 | Self-Governance | Change Panel | TBD | Elec | Metering Equipment Managers, RECCo, Code Manager | Solution Development | Solution Development completed | 2023-02-21
R0065 | Registration of Smart Export Guarantee (SEG) Sites | Link | Colette Baldwin | Code Manager | Elise Handy | 2022-08-22 | TBD | Low | 90 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0066 | Inclusion of SMRS Data Items in EES (BSC CP1568 Consequential Change) | Link | Gemma Dixon | Code Manager | Gemma Dixon | 2022-08-26 | 1b (Cat 1 products with technical impacts) | Low | 108 | Self-Governance | Change Panel | 2023-06-30 | Elec | EES Users | Awaiting Implementation | Implementation | 2023-06-30
R0067 | Introduction of CSS refresh functionality | Link | Michael Taylor | Code Manager | Elise Handy | 2022-08-26 | 2b (Cat 2 products with technical impacts) | Low | 109 | Self-Governance | Technical Expert Panel | 2023-06-30 | Gas | CSS Provider, Switching Data Service Providers, Energy Suppliers | Impact Assessment | Service Provider impact assessments to be re-visited and replanned, to take in to account the testing of the development will be in a different test environment | 2023-02-17
R0068 | REC Main Body Data Protection Changes | Link | Cordelia Grey | DCC | Jonathan Holland | 2022-09-02 | TBD | Low | 85 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0069 | Amendments to Sample Access Agreement | Link | Cordelia Grey | DCC | Jonathan Holland | 2022-09-02 | TBD | Low | 54 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0070 | Provision of Enduring Test Environments | Link | Beth Brown | Code Manager | Gemma Dixon | 2022-09-09 | TBD | Medium | 103 | Self-Governance | Change Panel | TBD | TBD | CSS Provider, Switching Operator | Impact Assessment | Service Provider PIA due back | 2023-03-03
R0071 | DCC access to EES and GES | Link | Cordelia Grey | DCC | TBC | 2022-09-12 | TBD | Low | 100 | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Data requirements to be confirmed by Change Proposer | 2023-02-24
R0072 | Introduction of a new Meter Asset Condition Code | Link | Clive Wicks | Consumer | Elise Handy | 2022-09-22 | TBD | Low | 76 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0073 | Housekeeping Change Process | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2022-09-27 | 1a (Cat 1 products without technical impacts) | Low | 76 | Self-Governance | Change Panel | 2023-04-01 | TBD | Code Manager, REC Parties and Service Providers | Final Assessment | Publication of Final Change Report | 2023-02-28
R0074 | Release of Community View Data Items to MEMs in GES | Link | Dave Addison | Xoserve | Elise Handy | 2022-09-29 | 2b (Cat 2 products with technical impacts) | High | 158 | Self-Governance | Technical Expert Panel | 2023-02-24 | Gas | Suppliers, Metering Equipment Managers, GES Provider | Final Assessment | TEP approval of the Final Change Report | 2023-02-22
R0075 | Enabling Software Product Qualification | Link | Elaine Eyles | ESG Global Ltd | Harriet Truss | 2022-10-07 | TBD | Low | 42 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0076 | DNOs notifying Suppliers about Crossed Meters | Link | Anne-Claire Leydier | UK Power Distribution | Gemma Dixon | 2022-10-07 | TBD | Low | 83 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0077 | Resolution of EES API SearchAddress method discrepancies | Link | Mark Pearce | Code Manager | Jonathan Holland | 2022-10-13 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | On Hold | Confirmation being sought on the exact requirements to be taken forward before the priority can be determined and a change plan can be developed. | 2023-02-28
R0078 | EMR Settlement Limited - additional access to EES | Link | Ben Lathbury | EMRS | Gemma Dixon | 2022-10-07 | TBD | Medium | 101 | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Code Manager to develop Change Proposal Plan following confirmation of priority from the Proposer | 2023-03-10
R0079 | Addition of Previous MEM to the EES API | Link | Adrian Salter | EDF | Jonathan Holland | 2022-11-04 | 2b (Cat 2 products with technical impacts) | Low | 74 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0080 | Improvements to ‘Failed to Deliver’ CSS Messages | Link | Cordelia Grey | DCC | Gemma Dixon | 2022-10-27 | TBD | Medium | 136 | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Technical discussions to be taken forward with Service Providers, ahead of Plan being set and IAs being taken forward | 2023-02-28
R0081 | CSS Market Message Retry Strategy | Link | Cordelia Grey | DCC | Gemma Dixon | 2022-10-27 | TBD | Medium | 136 | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Technical discussions to be taken forward with Service Providers, ahead of Plan being set and IAs being taken forward | 2023-02-28
R0082 | Formalising the Submission of PPMIP Unallocated Transaction Report (UTR) Files | Link | Rosalind Timperley | Code Manager | Jonathan Holland | 2022-11-28 | TBD | Low | 47 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0083 | Changes to Supply Number Format for MHHS | Link | Andrew Wallace | RECCo | Harriet Truss | 2022-12-02 | 2a (Cat 2 products without technical impacts) | High | 158 | Authority-Approval | Change Panel | TBD | Electricity | Suppliers, DNOs, TPIs | Initial Assessment | IAR and CPP presented to Change Panel for approval | 2023-02-21
R0083A | Changes to Supply Number Format for MHHS (Alternative) | Link | Andrew Wallace | RECCo | Harriet Truss | 2022-12-05 | 2a (Cat 2 products without technical impacts) | High | 158 | Authority-Approval | Change Panel | TBD | Electricity | Suppliers, DNOs, TPIs | Initial Assessment | IAR and CPP presented to Change Panel for approval | 2023-02-21
R0084 | Housekeeping changes to the approved legal text for R0047 | Link | Ann Perry | Code Manager | Ann Perry | 2022-12-16 | 1a (Cat 1 products without technical impacts) | Low | 78 | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Initial Assessment Report and Change Proposal Plan being present to the Change Panel for approval | 2023-02-21
R0085 | Switching Programme Designation of the Steady State Commencement Date | Link | Tina Pearce | Code Manager | Ann Perry | 2022-12-16 | 1a (Cat 1 products without technical impacts) | Low | 32 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0086 | ERDS Upload File in the Data Specification and clarification of cancellation code | Link | Ryan Dale | Code Manager | Gemma Dixon | 2022-12-16 | TBD | Low | 64 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0087 | MAP - GES Portfolio Dashboard | Link | David Newman | Correla Limited | Jonathan Holland | 2022-12-09 | TBD | Low | 33 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0088 | Make Shipper NExA values available on the GES portal | Link | Sharon Dudley | Xoserve | Ann Perry | 2023-01-12 | TBD | Medium | 101 | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Agree priority with the proposer and align activity with other cross code change | 2023-02-24
R0089 | Removal of Pre-COVID AQ Value from Data Access Matrix | Link | David Addison | Xoserve | Ann Perry | 2022-12-30 | TBD | Low | 32 | TBD | TBD | TBD | TBD | TBD | On Hold | Review priority and confirm it is appropriate for the change to remain on hold. | 2023-02-28
R0090 | Alignment of Data Specification with Pre-REC Rules and Consequential Impacts on R0011 Legal Text | Link | Rosalind Timperley | Code Manager | Gemma Dixon | 2023-01-18 | 2b (Cat 2 products with technical impacts) | Low | 91 | Self-Governance | Technical Expert Panel | TBD | Elec | Energy Suppliers, Generators and Capacity Providers | Initial Assessment | Present IAR/CPP to Change Panel | 2023-02-21
R0091 | Clarifications to the Theft Detection Incentive Schemes | Link | Andrew Waghorn | Code Manager | Elise Handy | 2023-01-23 | 1a (Cat 1 products without technical impacts) | Low | 87 | Self-Governance | Change Panel | 2023-04-01 | Elec and Gas | Suppliers, Code Manager | Preliminary Assessment | Consultation to be published | 2023-02-17
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | Link | Cordelia Grey | DCC | TBC | 2023-02-01 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Code Manager to discuss the change with the Proposer to agree priority and next steps | 2023-02-24
R0093 | Uplift to CSS Maximum Demand Volumes during MHHS Migration Period | Link | Jon Hawkins | RECCo | Harriet Truss | 2023-02-06 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Initial Assessment | Consolidated initial assessment triggered | 2023-02-24

## CP priority heatmap (hidden)
Urgency | 3
2
1
0
|  | 0 | 1 | 2 | 3
Significance
| R06 | R0006 - Missing Meter Technical Details
| R09 | R0009 - Introduction of SDEP and EES User Maintenance API
| R10 | R0010 - New Meter Types for Auxiliary Proportional Controllers (APCs)
| R15 | R0015 - Remote communication obligations for Advanced Meters
| R16 | R0016 - Resolution of Bilateral Erroneous Transfers
| R17 | R0017 - Invalid Requests for Site Technical Details
| R21 | R0021 - Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier
| R22 | R0022 - Amendment to REC Data Access Matrix
| R24 | R0024 - EAC information in the EES API
| R25 | R0025 - Service Provider Performance Charges (ERDS, GRDS, DCC)
| R26 | R0026 - Whole current (WC)/Current Transformer (CT) certificates
| R30 | R0030 - Erroneous Transfer Cancellations
| R32 | R0032 - New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS)
| R36 | R0036 - Housekeeping amendments
| R37 | R0037 - Housekeeping amendments - Prepayment Credit Balance & Debt Transfer Processes
| R40 | R0040 - CSS Switch Synchronisation to ERDA at SecuredActive |  |  |  | Awaiting Initial Assessment
| R43 | R0043 - Commissioning of Works using shared Meter Operator services by the Crowded Meter Room Co-ordinator (CMRC) |  |  |  | Awaiting Initial Assessment
| R44 | R0044 - MHHS Programme Changes required to Central Switching Service
| R45 | R0045 - Changes to SDEP Messages for REC V3.0
| R47 | R0047 - Metering Code of Practice Consolidation Review
| R48 | R0048 - DCC Service Organisation Control 2 (SOC2) Assessments |  |  |  | Awaiting Initial Assessment
| R49 | R0049 - Intellectual Property Rights and Services Data Main Body changes |  |  |  | Awaiting Initial Assessment
| R50 | R0050 - Clarification of REC Maintenance of Qualification Schedule |  |  |  | Awaiting Initial Assessment
| R51 | R0051 - Switch Request Objections (Change of Occupier) |  |  |  | Awaiting Initial Assessment
| R52 | R0052 - GES Service Definition Document
| R53 | R0053 - 24/7 Emergency Metering Service |  |  |  | Awaiting Initial Assessment
| R54 | R0054 - EES Access for Virtual Lead Parties
| R55 | R0055 - Switching Operator Outage Notification Lead Time
| R56 | R0056 - EES/GES Additional Service Request for Housing Associations to be added to the Data Access Matrix |  |  |  | Awaiting Initial Assessment
| R57 | R0057 - Clarification of Supplier of Last Resort Obligations under the REC |  |  |  | Awaiting Initial Assessment
| R58 | R0058 - REC Services Procurement Clarification |  |  |  | Awaiting Initial Assessment
| R59 | R0059 - Maintenance of Qualification Schedule Change |  |  |  | Awaiting Initial Assessment
| R60 | R0060 - ERDS Service Definition timezone correction |  |  |  | Awaiting Initial Assessment
| R61 | R0061 - Resolution of invalid CSS data by Data Owners |  |  |  | Awaiting Initial Assessment
| R62 | R0062 - Removal of ERDA meteringPointEnergyFlow change restriction |  |  |  | Awaiting Initial Assessment
| R63 | R0063 - Addition of key information to all Service Now tickets |  |  |  | Awaiting Initial Assessment
| R64 | R0064 - Creating a Meter Operator Agent and MOCoP Installer |  |  |  | Awaiting Initial Assessment
| R65 | R0065 - Registration of Smart Export Guarantee (SEG) Sites |  |  |  | Awaiting Initial Assessment
| R66 | R0066 - Inclusion of new DNO mastered SMRS Data Items in the EES. |  |  |  | Awaiting Initial Assessment
| R67 | R0067 - Introduction of CSS refresh functionality |  |  |  | Awaiting Initial Assessment
| R68 | R0068 -REC Main Body Data Protection Changes |  |  |  | Awaiting Initial Assessment
| R69 | R0069 - Amendments to Sample Access Agreement |  |  |  | Awaiting Initial Assessment
| R70 | R0070 - Provision of Enduring Test Environments |  |  |  | Awaiting Initial Assessment
| R71 | R0071 - DCC access to EES and GES |  |  |  | Awaiting Initial Assessment
| R72 | R0072 - Introduction of a new Meter Asset Condition Code |  |  |  | Awaiting Initial Assessment
| R73 | R0073 - Housekeeping Change Process |  |  |  | Awaiting Initial Assessment
| R74 | R0074 - Release of Community View Data Items to MEMs in GES |  |  |  | Awaiting Initial Assessment
| R75 | R0075 - Enabling Software Product Qualification |  |  |  | Awaiting Initial Assessment
| R76 | R0076 - DNOs notifying Suppliers about Crossed Meters |  |  |  | Awaiting Initial Assessment
R06
R10
R09
R16
R15
R25
R26
R17
R22
R21
R30
R32
R37
R36
R44
R47
R43
R54
R55
R52
R66

## Portfolio View
REC CHANGE PORTFOLIO Last updated: 12/02/2023
Priority Status and Score |  | ON HOLD | TO BE PRIORITISED / TRIAGED | CODE MANAGER'S INITIAL ASSESSMENT | SOLUTION DEVELOPMENT | IMPACT ASSESSMENT | PRELIMINARY ASSESSMENT | CONSULTATION | FINAL ASSESSSMENT | AWAITING AUTHORITY DETERMINATION | AWAITING IMPLEMENTATION
CRITICAL | 171
HIGH | 151 170
2
MEDIUM | 101 150
|  | 1 |  | 4 | 5 | 2
LOW | 0 100
|  | 16 | 0 | 6 | 3 | 1 | 2 | 1 | 2
TBD
|  | 1 | 3 | 2
|  | 18 | 3 | 12 | 8 | 3 | 2 | 1 | 4 | 0
R15
R21
R47
R32
R54
R30
R52
R55
R09
R66
R37
R17
R06
R16
R43
R44
R74
R64
R59
R70
R63
R67
R25
R57
R48
R49
R53
R51
R56
R72
R75
R73
R76
R77
R78
R10
R22
R11
24 February 2023
R58
R61
R60
R62
R65
R69
R68
R71
Key
On track
Progress at risk
Behind Plan
RXX
RXX
RXX
1 April 2023
30 June 2023
Technical elements only
date TBC
R79
R72
R82
R83
R83A
R84
R85
R86
R87
R88
R89
R80
R81
R92
R91
R90
R93
R26

## Withdrawn CPs
Change Proposal Reference | Date Submitted | Date Proposer withdrew support | Fully Withdrawn from Process | Change Proposal Title | Proposer Name | Proposer Company
R0005 | 2021-09-06 | 2021-10-04 | 2021-10-18 | Access to EES (Energy Enquiry Service) and GDCC API for CSS Interface Providers | Karen Lee | ESG Global Ltd
R0007 | 2021-09-08 | 2021-12-10 | 2021-12-24 | Changes to message ownership in SDEP | Rachel Norberg | Utilita
R0013 | 2021-10-08 | 2021-01-14 | 2021-01-31 | Electricity Enquiry Service API Service Status | Andrew Long | Switchcraft
R0004 | 2021-09-02 | 2022-01-21 | 2022-02-07 | Electricity Enquiry Service (EES) Master Administration User (MAU) Access | Diane Lyon | Scottish Power Energy Retail
R0029 | 2022-01-11 | 2022-02-18 | 2022-03-04 | Mandating Timely Meter Product Data (MPD) Updates | Rosalind Timperley | Code Manager
R0027 | 2022-01-06 | 2022-04-14 | 2022-04-14 | Minimum identification requirements in the Meter Operation Code of Practice | Courtney Campbellwood | Code Manager
R0046 | 2022-05-21 | 2022-07-04 | 2022-07-19 | Governance of Data under the REC | Brian O'Shea | RECCo
R0024 | 2021-12-10 | N/A | 2022-08-29 | EAC information in the EES API | Andrew Long | Switchcraft
R0050 | 2022-05-17 | 2022-10-28 | 2022-10-28 | Clarification of REC Maintenance of Qualification Schedule | Bryan Heap | ENWL
R0040 | 2022-03-16 | 2022-11-03 | 2022-11-17 | CSS Switch Synchronisation to ERDA at SecuredActive | Daniel Tadecicco | St Clements

## Rejected CPs
Date Raised | Date Rejected | Change Proposer | Change Proposer's company | Change Proposal Title | Change Proposal Description | Rejection Reason | Next steps / Actions taken
2021-09-08 | 2021-09-08 | Richard Hill | British Gas | Cross Polarity Reporting Guidance | Guidance has previously been discussed and developed under MOCOPA on cross polarity reporting, to ensure Meter Operators (on behalf of Suppliers) inform the relevant party of a cross polarity incident when they are NOT the incumbent Supplier. At present the reporting is ad-hoc on a bi-lateral basis between Meter Operators, Suppliers or DNOs A one page flow diagram had previously been discussed and approved by affected parties at MOCOPA and DCUSA and accepted as useful guidance. | The submission was proposing the introduction of guidance. The REC was drafted under the principle that guidance would not be included in Schedules alongside obligations. Therefore, the standard change process is not the appropriate mechanism for the introduction of guidance. At present the reporting is ad-hoc on a bi-lateral basis between Meter Operators, Suppliers or DNOs A one page flow diagram had previously been discussed and approved by affected parties at MOCOPA and DCUSA and accepted as useful guidance. | In agreement with the Change Proposer, the Change Proposal has been rejected and a Category 3 Change Proposal has been raised. A paper will be presented to the Metering Expert Panel, to review the previously prepared guidance and agree appropriate next steps for the introduction of the guidance.
2021-10-06 | 2021-10-07 | David Harper | Gastech Engineering Limited | Addition of a new meter model to Market Domain Data (MDD) | A new meter model has been specified for a non-standard site. The meter model and attributes need to be added to the MDD. A standard Change Proposal was raised to update the MDD Meter Product Table. | The standard Change Proposal is not the appropriate mechanism for progressing changes to Market Domain Data. The Meter Product data is part of the REC Data Specification and a separate, proportionate, process has been defined (similar to that utilised under SPAA). | In agreement with the Proposer, the Change Proposal has been rejected and the Proposer has been provided with the Meter Product Change Request Form. The Proposer will submit the completed form, to progress the change to MDD.
2021-11-10 | 2021-11-11 | Douglas Alexander | Elexon | Amendment to RECMEP Terms of Reference to allow Elexon Representative voting rights | The Elexon attendee at the REC Metering Expert Group has no voting rights. Although Elexon have been proactive in providing feedback based on our expertise of SVA Metering, we are just observers and committee would lose out on the technical knowledge and practical experience if we reverted to merely observing. With no vote it is effectively providing free consultancy and a lack of recognition of Elexon reps expertise in SVA Metering. | This submission proposes a potential change to the REC Metering Expert Panel Terms of Reference - this is a Category 3 document under responsibility of the REC Change Panel. The standard Change Proposal process is not the appropriate mechanism for the progression of this change. | This issue has been discussed with the proposer, RECCo and the Code Manager. No changes to the Metering Expert Panel ToR are proposed at this time.
2021-12-03 | 2021-12-06 | Liam Gatens | South Tyneside Homes | Relying on using Electrical Suppliers for Emergency and Planned Double pole isolator works | Allowing the previous accredited MOCOPA approved companies to be able to install new and repair existing Double pole isolators in domestic and communal properties, without the inclusion of the associated electrical supplier. This would also allow a emergency response service for high priority works by using procured companies. | This submission is covered by DCP 394 and the related REC change which the Code Manager is due to raise. Proposed agreed for this submission to be rejected and a REC Change raised that covers all elements required. | R0021 has been raised to progress the REC changes
2022-05-03 | 2022-05-06 | Greg Wedge | E.ON | SMICoP Microbusiness Quarterly Performance Reporting | To introduce the production of the SMICoP MB quarterly performance reports like what is currently done for Residential. | This is a duplication of a Change Proposal that is already in flight, R0033 | No further action - R0033 will progress
2022-09-21 | 2022-09-22 | Jo Hargeaves | British Gas | SDEP - New field for MSR - Multiple Supplier Report | Within the SDEP portal under process type PT0023 there is no clear way to differentiate between a mis-directed payment task and a multiple supplier report task, without first opening and reading the communication. If MSR tasks and MDP tasks were separated out it would make the completion of the work required much simpler and quicker to complete, resulting a much more timely resolution for customers and a better customer outcome. | This issue has been absorbed in to the SDEP review that is currently in flight | RTS have confirmed this has been included in the scope of the review - no further action required

## Implemented
Change Proposal Reference | Change Proposal Title | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Priority Status | Change Path | Responsible Committee | Proposed Implementation Date | Fuel | Impacted Parties | Process Stage | Next Activity | Next Activity Due Date | On Track (RAG)
R0001 | Amendment to DCC Service Flag (DI51130) Data Item | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-09-01 | 2 |  | Self-Governance | Change Panel | 2021-11-04 | Elec and gas | n/a | Implemented
R0002 | Review of Data Specification Category in REC Baseline Statement | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-09-01 | 2 |  | Self-Governance | Change Panel | 2021-11-04 | n/a | n/a | Implemented
R0003 | Market-wide Half-Hourly Settlement Implementation | Link | Abid Sheikh | Ofgem | Jonathan Hawkins | 2021-09-01 | 1 |  | Authority-Approval | Change Panel | 2021-11-04 | Elec | n/a | Implemented
R0008 | Consequential New and Amended Market Messages for BSC Modification P375 | Link | Gemma Dixon | Code Manager | Gemma Dixon | 2021-09-08 | 2 | High | Self-Governance | Technical Expert Panel | 2022-06-30 | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers Data Collectors Data Aggregators | Implemented
R0012 | Housekeeping amendments to REC V2 | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-10-04 | 1 |  | Self-Governance | Change Panel | 2022-01-31 | n/a | n/a | Implemented
R0014 | Cable Colour Identification | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2021-11-01 | 2 | Low | Self-Governance | Metering Expert Panel | 2022-06-30 | Elec and Gas | Distribution Network Operators Metering Equipment Managers | Implemented
R0019 | Consequential REC Changes for BSC CP1532 | Link | Ann Perry | Code Manager | Ann Perry | 2021-11-26 | 1 | Low | Self-Governance | Metering Expert Panel | 2022-06-30 | Elec | Energy Suppliers Metering Equipment Managers | Implemented
R0020 | ETTOS Report Dissemination | Link | Aiyesha Andrade | RECCo | Ann Perry | 2021-11-29 | 1 |  | Self-Governance | Change Panel | 2022-01-31 | n/a | n/a | Implemented
R0023 | Prepayment Unallocated Transactions | Link | Jonathan Holland | Code Manager | Jonathan Holland | 2021-12-15 | 1 | Low | Self-Governance | Change Panel | 2022-06-30 | Elec and Gas | Energy Suppliers Prepayment Meter Infrastructure Provider | Implemented
R0028 | Review of Category 3 documents in the REC Baseline Statement | Link | Anton Moden | Code Manager | Ann Perry | 2022-01-07 | 2 | Medium | Self-Governance | Change Panel | 2022-04-14 | n/a | n/a | Implemented
R0034 | Market Stabilisation Charge | Link | Henry Kemp | Ofgem | Ann Perry | 2022-02-17 | 1 | High | Authority Determined | Change Panel | 2022-04-14 | Elec and gas | n/a | Implemented
R0035 | Market Stabilisation Charge - Administration | Link | Jon Dixon | RECCo | Ann Perry | 2022-02-21 | 1 | High | Authority Determined | Change Panel | 2022-06-30 | Elec and Gas | Energy Suppliers | Implemented
R0038 | Performance Assurance Report Catalogue Changes as a consequence of REC V3.0 | Link | Lewis Williams | Code Manager | Gemma Dixon | 2022-03-23 | 2 | TBD | Self-Governance | Change Panel | 2022-07-18 | n/a | Energy Suppliers Metering Equipment Managers | Implemented
R0039 | Revised Implementation Date for R0011 | Link | Patrick Bibby | LCCC | Gemma Dixon | 2022-03-25 | 2 |  | Self-Governance | Change Panel | 2022-06-01 | Elec | Energy Suppliers | Implemented
R0041 | REC V3.0 | Link | Alasdair MacMillan | Ofgem | Ann Perry | 2022-04-07 | 1 | High | Authority Determined | Change Panel | 2022-07-18 | Elec and Gas | Energy Suppliers Distribution Network Operators Gas Transporters Metering Equipment Managers DCC EES Users GES Users | Implemented
R0042 | Performance Assurance Board Terms of Reference | Link | Eliana Campbell | Code Manager | Jonathan Holland | 2022-04-14 | 2 | High | Self-Governance | Change Panel | 2022-07-18 | n/a | Central Switching Service Provider Electricity Enquiry Service Provider Gas Enquiry Service Provider Electricity Ratal Data Service Gas Retail Data Service | Implemented
R0045 | Changes to SDEP Messages for REC V3.0 | Link | Jon Hawkins | RECCo | Gemma Dixon | 2022-05-06 | 2 | High | Self-Governance | Technical Expert Panel | 2022-07-18 | Elec and Gas | Energy Suppliers Distribution Network Operators | Implemented
R0046A | Governance of Data under the REC (Alternative) | Link | Brian O'Shea | RECCo | Jonathan Holland | 2022-05-21 | 1 | High | Authority Determined | Change Panel | 2022-08-03 | n/a | DCC | Implemented
R0018 | Complex Sites process improvements | Link | Ann Perry | Code Manager | Jonathan Holland | 2021-11-25 | 1a (Cat 1 products without technical impacts) | low | Self-Governance | Metering Expert Panel | 2022-11-04 | Elec | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | Implemented
R0031 | Altering the Trigger Points for CT Commissioning | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2022-01-26 | 2b (Cat 2 products with technical impacts) | low | Self-Governance | Metering Expert Panel | 2022-11-04 | Elec | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | Implemented
R0033 | Micro-business Smart Meter Installation Reports | Link | Kelly Austin | EDF | Colette Baldwin | 2022-01-31 | 1a (Cat 1 products without technical impacts) | low | Self-Governance | Change Panel | 2022-11-04 | Elec and Gas | Energy Suppliers, Distribution Network Operators, Metering Equipment Managers | Implemented
R0036 | Extensive Housekeeping amendments | Link | Ann Perry | Code Manager | Jonathan Holland | 2022-03-04 | 1a (Cat 1 products without technical impacts) | Medium | Self-Governance | Change Panel | 2022-11-04 | n/a | Energy Suppliers | Implemented